## Worksheet
Growth Planning - Time Tracker
Planning View ¦ Period: Q2 2024
Activity / Goal | Weekly Breakdown |  |  |  | Total Hours | Progress % | Status
| Week 1 (Apr 1-7) | Week 2 (Apr 8-14) | Week 3 (Apr 15-21) | Week 4 (Apr 22-28)
Market Research Phase | 8 | 10 | 6 | 4 | 28 | 70% | Pending Review
User Persona Development | 6 | 7 | 9 | 5 | 27 | 80% | In Progress
Campaign Strategy Design | 5 | 6 | 8 | 7 | 26 | 65% | In Progress
Milestone Planning & Roadmap | 4 | 5 | 7 | 6 | 22 | 55% | In Progress
Digital Outreach Campaign Setup | 6 | 8 | 10 | 7 | 31 | 95% | Pending Approval
Analytics & KPI Dashboard | 5 | 4 | 6 | 8 | 23 | 75% | In Progress
Total Hours for Q2 | 34 | 40 | 46 | 37 | 157 | N/A | N/A
Projected Completion (May 31) | Estimated completion rate: 87% ¦ Remaining effort: 24 hours |  |  |  |  | 87% | On Track