## Worksheet
Growth Planning - Startup To-Do List
Track key initiatives to fuel scalable growth
Task | Description | Owner | Due Date | Priority | Status
Launch MVP Landing Page | Create high-converting landing page with CTA and user signup form | Alex Johnson | 2024-05-15 | High | Not Started
Develop Core Feature Set | Implement primary product functionality based on user feedback loop | Sophie Chen | 2024-06-30 | High | In Progress
Setup Analytics Dashboard | Integrate Google Analytics and Mixpanel for user behavior tracking | Michael Torres | 2024-05-20 | Medium | In Progress
Build Beta User Community | Recruit 100 early adopters through social media and influencer outreach | Lisa Patel | 2024-06-15 | Medium | Not Started
Conduct User Feedback Sessions | Host weekly interviews with 5 beta users to gather qualitative insights | James Wilson | 2024-07-31 | Low | Not Started
Optimize Conversion Funnel | Improve signup-to-activation rate by A/B testing key UI elements | Emma Rodriguez | 2024-08-15 | High | Not Started
Secure First Round Funding | Prepare pitch deck and reach out to 50 angel investors and VCs | David Kim | 2024-07-31 | High | In Progress
Implement Onboarding Flow | Create guided tutorial for new users with interactive walkthroughs | Grace Lee | 2024-06-10 | Medium | Not Started
Expand Marketing Channels | Launch paid campaigns on Google Ads and LinkedIn targeting startups | Tom Harris | 2024-08-31 | Medium | Not Started
Develop Growth Metrics Dashboard | Build real-time dashboard showing DAU, retention, conversion rates | Anna Wu | 2024-07-15 | High | Not Started