## Worksheet
Habit Building Project Plan
Purpose: Habit Building ¦ Template Type: Project Plan ¦ Style/Version: Large Business
Phase | Activity/Task | Owner | Start Date | End Date | Status | Milestones & Deliverables
Phase 1: Foundation & Planning (Weeks 1–4)
Foundation | Define core habits and success metrics | Alice Chen, PMO | 2024-07-01 | 2024-07-15 | Completed | Clear habit KPIs, success definition document, stakeholder sign-off.
Foundation | Establish project governance and roles | Ryan Foster, CIO | 2024-07-03 | 2024-07-18 | In Progress | Governance framework, RACI matrix, kickoff meeting.
Phase 2: Design & Development (Weeks 5–8)
Design | Create habit tracking dashboard prototype | Samira Patel, UX Lead | 2024-07-19 | 2024-08-08 | In Progress | Interactive prototype with user feedback integration.
Development | Integrate habit reminder engine and calendar sync | Jacob Lin, Engineering Lead | 2024-07-26 | 2024-08-15 | Delayed | Core integration tested; dependency on third-party API.
Phase 3: Testing & Validation (Weeks 9–12)
Testing | Conduct UAT with pilot group of 50 employees | Lena Dubois, QA Manager | 2024-08-16 | 2024-08-31 | Completed | Feedback report with 94% satisfaction score.
Phase 4: Rollout & Feedback (Weeks 13–16)
Rollout | Deploy to all departments with onboarding training | Marcus Lee, HR Transformation | 2024-09-01 | 2024-09-15 | In Progress | Training modules created; 78% employee enrollment.
Feedback | Collect post-launch habit adoption data and insights | Sophia Wu, Data Insights | 2024-09-16 | 2024-10-31 | Completed | Monthly habit tracking reports, engagement trends.
Overall Status: |  | 85% Complete – On Track (Minor Delays in Dev) |  |  | Next Review: September 20, 2024