## Worksheet
Habit Building Project Plan
Task | Responsible | Start Date | End Date | Status | Milestone
Define core daily habits for team members | Jane Smith, Team Lead | 2023-10-01 | 2023-10-05 | In Progress | Habit Framework Defined
Create habit tracking dashboard | Mike Johnson, IT Specialist | 2023-10-06 | 2023-10-15 | Not Started | Dashboards Live & Tested
Conduct habit initiation workshop | Sarah Lee, HR Manager | 2023-10-16 | 2023-10-17 | Not Started | Workshop Completed & Feedback Collected
Launch 3-week pilot program | All Team Members | 2023-10-18 | 2023-11-05 | Not Started | Pilot Success Metrics Achieved
Evaluate pilot results and adjust habits | Jane Smith, Team Lead | 2023-11-06 | 2023-11-10 | Not Started | Pilot Feedback Analyzed & Plan Updated
Implement permanent habit system | All Team Members, IT Support | 2023-11-13 | 2023-11-30 | Not Started | Habit System Fully Operational