## Worksheet
Habit Building - Startup Project Plan
Task ID | Task Description | Owner | Start Date | Due Date | Status
#HB-001 | Define core habits for team productivity | Alice Johnson | 2024-04-01 | 2024-04-05 | In Progress
#HB-002 | Create daily habit tracking dashboard | Michael Chen | 2024-04-03 | 2024-04-15 | In Progress
#HB-003 | Develop habit reminders system (mobile & web) | Sarah Kim | 2024-04-10 | 2024-04-25 | Pending
#HB-004 | Implement weekly review & analytics feature | James Wilson | 2024-04-15 | 2024-05-10 | Pending
#HB-005 | Conduct user testing with 25 beta users | Lisa Martinez | 2024-04-18 | 2024-05-18 | Pending
#HB-006 | Integrate feedback into final product version | Alice Johnson | 2024-05-19 | 2024-06-15 | Pending