## Worksheet
Habit Building Project Timeline - Team Use
Task ID | Task Description | Owner(s) | Start Date | End Date | Status
T001 | Define daily habit goals for team members (e.g., morning journaling, 30-min walk) | Jane Doe, Mark Lee | 2024-04-01 | 2024-04-05 | In Progress
T002 | Create habit tracking template (Google Sheets / Notion) | Sam Chen | 2024-04-03 | 2024-04-15 | Pending
T003 | Onboard team to habit tracking system (training session) | Lisa Park | 2024-04-16 | 2024-04-18 | Pending
T004 | Launch 3-week habit challenge (daily check-ins via Slack) | All Team Members | 2024-04-19 | 2024-05-10 | Pending
T005 | Weekly review: analyze tracking data, celebrate wins, adjust habits | Jane Doe (Facilitator) | 2024-04-26 | 2024-05-17 | Pending
T006 | Publish team habit report and share insights (presentation & document) | Mark Lee, Sam Chen | 2024-05-18 | 2024-05-25 | Pending
Last updated: April 5, 2024 ¦ Project Duration: April 1 – May 25, 2024