## Worksheet
Home Management Business Plan - Tracking View
Project Phase | Objective/Task | Owner | Start Date | Target End Date | Status | Budget (USD) | Progress (%)
Planning & Research | Develop home budget framework and long-term financial goals | Jane Doe | 2024-05-01 | 2024-06-15 | High Priority | $8,500 | 75%
Renovations & Repairs | Update kitchen appliances and flooring (Phase 1) | Mike Smith | 2024-06-10 | 2024-08-30 | In Progress | $15,750 | 45%
Energy Efficiency | Install solar panels and smart thermostat system | Lisa Chen | 2024-07-01 | 2024-11-30 | In Progress | $28,900 | 35%
Home Security Upgrade | Install security cameras, smart locks, and alarm system | Tom Johnson | 2024-06-15 | 2024-07-31 | Low Priority | $6,350 | 95%
Furniture & Interior Design | Select and order new living room and bedroom furniture set | Sarah Lee | 2024-08-01 | 2024-10-15 | High Priority | $12,400 | 65%
Landscaping & Exterior | Plant garden beds and install irrigation system | Alex Rivera | 2024-09-10 | 2024-11-30 | In Progress | $5,600 | 55%
Total Budget Spent: | [5 empty] | $77,500 | 62%