## Worksheet
Home Management - Gantt Chart (Analysis View)
Task | Owner | Status | Start Date | End Date | Duration (days)
Home Renovation Planning | John Doe | In Progress | 2024-01-15 | 2024-01-30 | 16
Design Approval | Jane Smith | Completed | 2024-01-31 | 2024-02-15 | 15
Contractor Selection | Mike Brown | Not Started | 2024-02-16 | 2024-03-15 | 30
Demolition Work | Team Alpha | Not Started | 2024-03-16 | 2024-03-31 | 16
Plumbing & Electrical | Team Beta | Not Started | 2024-04-01 | 2024-05-15 | 45
Interior Finishing | Team Gamma | Not Started | 2024-05-16 | 2024-06-30 | 45
Final Inspection & Handover | John Doe | Not Started | 2024-07-01 | 2024-07-15 | 15
Legend: