## Worksheet
Home Management Gantt Chart - Detailed
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status | Progress (%)
001 | Interior Design Planning | 2024-04-01 | 2024-04-15 | 15 | In Progress
002 | Contractor Selection & Hiring | 2024-04-16 | 2024-04-30 | 15 | In Progress
003 | Structural Renovation (Walls, Floors) | 2024-05-01 | 2024-06-15 | 46 | In Progress
004 | Electrical & Plumbing Work | 2024-06-16 | 2024-07-15 | 30 | Not Started
005 | Drywall Installation & Painting | 2024-07-16 | 2024-08-15 | 31 | Not Started
006 | Flooring & Tiling Installation | 2024-08-16 | 2024-09-15 | 31 | Not Started
007 | Furniture & Fixtures Procurement | 2024-09-16 | 2024-10-15 | 30 | Not Started
008 | Interior Styling & Final Touches | 2024-10-16 | 2024-11-15 | 31 | Not Started
M01 | Completion & Handover | 2024-11-30 | 2024-11-30 | 1 | Milestone
Total Duration (End to End) | [5 empty] | 275 days
Legend:
■Progress bar indicates task progress.
Milestonetasks are marked in bold pink.