## Worksheet
Home Management Gantt Chart
Large Business Style ¦ Project Timeline Overview
Task / Milestone | Start Date | End Date | Duration (Days) | Progress | Responsible
Project Initiation & Planning | 2024-04-01 | 2024-04-15 | 15 |  | John Smith
Design & Architecture Phase | 2024-04-16 | 2024-05-15 | 30 |  | Sarah Johnson
Milestone: Design Approval | 2024-05-15 | 2024-05-15 | 1 |  | Project Board
Home System Integration | 2024-05-16 | 2024-07-15 | 60 |  | Mike Rodriguez
Smart Device Deployment | 2024-07-16 | 2024-08-31 | 47 |  | Lisa Chen
Milestone: System Testing Complete | 2024-08-31 | 2024-08-31 | 1 |  | QA Team
Final Configuration & Training | 2024-09-01 | 2024-09-15 | 15 |  | Alex Turner
Milestone: Go Live & Handover | 2024-09-15 | 2024-09-15 | 1 |  | Executive Team
Post-Implementation Review | 2024-09-16 | 2024-09-30 | 15 |  | John Smith
In ProgressMilestoneCritical Path
This Gantt Chart is for internal use only. © 2024 Home Management Solutions. All rights reserved.