## Worksheet
Home Management - Gantt Chart (Page 1)
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status
HM-001 | Initial Planning & Budgeting | 2024-06-15 | 2024-06-30 | 15
HM-002 | Home Inspection & Assessment | 2024-07-15 | 2024-07-31 | 16
HM-003 | Design & Interior Planning | 2024-08-15 | 2024-10-15 | 61
HM-004 | Contractor Selection & Approval | 2024-10-16 | 2024-11-30 | 45
HM-005 | Renovation & Construction Phase | 2024-12-15 | 2025-03-31 | 107
M-001 | Construction Start Date | 2024-12-15 | 2024-12-15 | N/A | Milestone
Page 1 of Multi-Page Gantt Chart ¦ Home Management Project Timeline ¦ Generated on June 5, 2024
Home Management - Gantt Chart (Page 2)
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status
HM-006 | Furnishings & Decor Procurement | 2025-04-15 | 2025-06-30 | 77
HM-007 | Interior Styling & Final Touches | 2025-07-15 | 2025-08-31 | 46
HM-008 | Final Inspection & Approval | 2025-09-15 | 2025-10-15 | 31
HM-009 | Move-In Preparation & Cleanup | 2025-10-16 | 2025-11-30 | 45
M-002 | Move-In Completion Date | 2025-11-30 | 2025-11-30 | N/A | Milestone
Page 2 of Multi-Page Gantt Chart ¦ Home Management Project Timeline ¦ Generated on June 5, 2024
Home Management - Gantt Chart (Page 3)
Task ID | Task Name | Start Date | End Date | Duration (Days) | Status
HM-010 | Post-Move-In Review & Feedback | 2025-12-01 | 2025-12-31 | 30
HM-011 | Home Systems Setup (Smart Home, Utilities) | 2025-07-30 | 2025-09-30 | 63
HM-012 | Landscaping & Exterior Updates | 2025-03-01 | 2025-05-31 | 91
HM-013 | Insurance & Legal Documentation Finalization | 2024-06-15 | 2025-04-30 | - (Ongoing)
M-003 | Project Completion Date | 2025-12-31 | 2025-12-31 | N/A | Milestone