## Home Management Gantt Chart
Home Management Gantt Chart
Task | Start Date | End Date | Status | Progress
Plan Home Renovation | 2024-01-05 | 2024-01-15 | In Progress | 60%
Order Materials | 2024-01-16 | 2024-01-31 | Pending | 0%
Paint Living Room | 2024-02-01 | 2024-02-15 | Pending | 0%
Install New Kitchen Cabinets | 2024-02-16 | 2024-03-15 | Pending | 0%
Update Flooring | 2024-03-16 | 2024-04-15 | Pending | 0%
Final Inspections & Clean-up | 2024-04-16 | 2024-04-30 | Pending | 0%
Move Back Into Home | 2024-05-01 | 2024-05-15 | Pending | 0%