## Worksheet
Home Management - Planning View Gantt Chart
Task | Start Date | End Date | Duration (Days) | Progress
Plan Renovation Timeline | 2024-01-15 | 2024-01-31 | 17
Design Kitchen Layout | 2024-02-01 | 2024-02-15 | 15
Order Kitchen Cabinets | 2024-02-16 | 2024-03-15 | 30
Demolition Phase | 2024-03-16 | 2024-03-31 | 16
Install Plumbing & Electrical | 2024-04-01 | 2024-04-15 | 15
Framing & Drywall | 2024-04-16 | 2024-05-15 | 30
Paint Interior Walls | 2024-05-16 | 2024-05-31 | 16
Lay Flooring | 2024-06-01 | 2024-06-15 | 15
Install Countertops & Fixtures | 2024-06-16 | 2024-07-15 | 30
Clean & Inspect Final Work | 2024-07-16 | 2024-07-31 | 16
Completion Date | 2024-07-31
Note:This is a planning view Gantt chart for home management. Progress percentages are illustrative and subject to change.