## Home Management Gantt Chart
Home Management Gantt Chart
Task Name | Start Date | End Date | Duration (Days) | Status | Progress
Renovation Planning | 2023-09-01 | 2023-09-15 | 15 | In Progress
Wall Painting | 2023-09-16 | 2023-09-30 | 15 | In Progress
Flooring Installation | 2023-10-01 | 2023-10-15 | 15 | Delayed
Light Fixture Installation | 2023-10-16 | 2023-10-25 | 10 | Completed
Furniture Assembly & Placement | 2023-10-26 | 2023-11-05 | 10 | In Progress
Final Cleaning & Inspection | 2023-11-06 | 2023-11-10 | 5 | In Progress
Move-In Preparation | 2023-11-11 | 2023-11-15 | 5 | In Progress
Full Home Handover | 2023-11-16 | 2023-11-16 | 1 | Completed
Total Duration | 2023-09-01 to 2023-11-16 (77 days) |  | 77 | Overall Progress: 68%