## Worksheet
Home Management Gantt Chart - Tracking View
Task | Owner | Start Date | End Date | Status | Progress (%)
Draft Home Renovation Plan | John Doe | 2023-10-01 | 2023-10-15 | Completed
Get Contractor Quotes | Jane Smith | 2023-10-16 | 2023-10-30 | In Progress
Finalize Renovation Contract | John Doe | 2023-10-31 | 2023-11-07 | In Progress
Start Demolition Work | Mike Johnson | 2023-11-08 | 2023-11-15 | Not Started
Electrical and Plumbing Updates | Mike Johnson | 2023-11-16 | 2023-12-05 | Not Started
Renovation Kickoff - Site Ready | Project Manager | 2023-11-08 | 2023-11-08 | Milestone Achieved
Wall Framing and Drywall | Mike Johnson | 2023-12-06 | 2024-01-15 | Not Started
Painting and Finishing | Jane Smith | 2024-01-16 | 2024-02-15 | Not Started
Renovation Completion - Final Inspection | Project Manager | 2024-02-15 | 2024-02-15 | Milestone Pending
Legend:
Completed- Task finished successfully.
In Progress- Ongoing task with active status.
Milestone- Key event or checkpoint in the project timeline.