## Worksheet
Home Management - Advanced Project Plan
Task ID | Task Description | Assigned To | Start Date | Due Date | Status | Prioritization | Budget (USD)
TK-001 | Complete kitchen renovation including cabinetry, countertop installation, and new appliances | Jane Smith | 2024-10-05 | 2024-11-30 | In Progress | High | $8,500.00
TK-002 | Remodel master bathroom with walk-in shower, new vanity, and lighting upgrade | Michael Brown | 2024-10-15 | 2024-12-15 | In Progress | High | $6,750.00
TK-003 | Landscaping overhaul including sodding, irrigation system installation, and flower beds | Sophia Lee | 2024-11-01 | 2024-11-30 | In Progress | Medium | $2,800.00
TK-004 | Professional roof inspection followed by repair of damaged shingles and gutter cleaning | Robert Johnson | 2024-11-15 | 2024-12-05 | Delayed (Weather) | High | $3,400.00
TK-005 | Install smart thermostat, LED lighting throughout the house, and upgrade insulation | Alex Turner | 2024-11-10 | 2024-12-31 | In Progress | Medium | $5,900.00
TK-006 | Install full home security system with cameras, motion sensors, and smart doorbell | Lisa Chen | 2024-12-01 | 2024-12-18 | In Progress | High | $3,600.00
TK-007 | Paint all interior walls and trim in living room, dining room, and hallways | Maria Garcia | 2024-11-25 | 2024-12-10 | In Progress | Low | $1,750.00
TK-008 | Organize basement, attic, and garage with shelving units and labeling system | Jennifer White | 2024-12-15 | 2025-01-10 | Not Started | Medium | $950.00
Total Project Cost: | [6 empty] | $34,650.00