## Worksheet
Home Management - Project Plan - Analysis View
Task ID | Task Description | Owner | Status | Start Date | End Date | Progress (%)(0-100)
TASK-001 | Renovate Kitchen Area | John Doe | In Progress | 2024-04-01 | 2024-06-15 | 65%
TASK-002 | Install Smart Home System | Jane Smith | In Progress | 2024-04-15 | 2024-07-30 | 35%
TASK-003 | Paint Living Room Walls | Mike Johnson | Completed | 2024-03-10 | 2024-03-15 | 100%
TASK-004 | Landscape Garden Area | Sarah Brown | In Progress | 2024-05-01 | 2024-08-31 | 75%
TASK-005 | Replace Old Roof Tiles | David Wilson | Delayed | 2024-04-18 | 2024-06-30 | 55%
TASK-006 | Clean and Organize Basement | Lisa Garcia | Completed | 2024-03-25 | 2024-03-31 | 100%
Last Updated: April 5, 2024 ¦ Project Status Analysis View