## Worksheet
Home Management - Annual Project Plan
Quarter | Project Phase | Main Tasks | Responsible Person | Status | Deadline (YYYY-MM-DD) | Budget (USD)
Q1 (Jan-Mar) | Planning & Assessment | Review current home condition, set annual goals, prioritize projects | Jane Smith | In Progress | 2024-03-31 | $500.00
|  | Conduct home safety inspection | Jane Smith | Completed | 2024-01-15 | $75.00
|  | Update home maintenance checklist | Mark Johnson | In Progress | 2024-02-15 |  | $100.00
Q2 (Apr-Jun) | Renovation & Upgrades | Kitchen remodeling and appliance upgrade | David Lee | To Do | 2024-06-30 | $5,200.00
|  | Replace kitchen cabinets and countertops | David Lee | Pending Approval | 2024-05-15 | $3,800.00
Q3 (Jul-Sep) | Energy Efficiency Projects | Install solar panels and upgrade insulation | Laura Chen | To Do | 2024-09-30 | $8,750.00
|  | Research and select solar panel provider | Laura Chen | In Progress | 2024-07-15 | $250.00
Q4 (Oct-Dec) | Maintenance & Review | Annual home maintenance and year-end review | Jane Smith | To Do | 2024-12-31 | $1,800.00
|  | Service HVAC system and clean gutters | Mark Johnson | To Do | 2024-11-30 | $650.00
Total Annual Budget: | [5 empty] | $16,250.00