## Home Management - Project Plan
Home Management - Project Plan
Task ID | Task Description | Assigned To | Status | Start Date | End Date | Budget (USD)
#001 | Kitchen Renovation - Demolition & Planning | John Smith | Completed | 2024-04-01 | 2024-04-15 | $3,500.00
#002 | Install New Kitchen Cabinets & Countertops | Mike Johnson | In Progress | 2024-04-16 | 2024-05-10 | $8,750.00
#003 | Electrical & Plumbing Upgrades | Sarah Lee | Pending | 2024-05-11 | 2024-05-31 | $4,200.00
#004 | Installation of Appliances (Fridge, Oven, Microwave) | Robert Brown | Pending | 2024-06-01 | 2024-06-15 | $3,800.00
#005 | Final Inspection & Cleanup | Linda Davis | Pending | 2024-06-16 | 2024-06-30 | $1,500.00
Total Project Budget:$21,750.00
Last Updated: April 5, 2024