## Worksheet
Home Management - Project Plan (Client View)
Task ID | Task Description | Owner | Start Date | End Date | Status | % Complete
TP-001 | Initial Home Assessment & Planning | John Doe | 2023-10-05 | 2023-10-12 | Completed | 100%
TP-002 | Kitchen Renovation - Demolition | Jane Smith | 2023-10-15 | 2023-10-25 | In Progress | 65%
TP-003 | Bathroom Remodeling - Plumbing & Tiling | Mike Johnson | 2023-10-26 | 2023-11-15 | In Progress | 40%
TP-004 | Electrical System Upgrade | Sarah Williams | 2023-11-16 | 2023-11-30 | Delayed | 5%
TP-005 | Interior Painting - Living Room & Hallways | Chris Brown | 2023-12-01 | 2023-12-14 | Completed | 100%
TP-006 | Flooring Installation - Hardwood & Tile | Lisa Garcia | 2023-12-15 | 2024-01-15 | In Progress | 70%
TP-007 | Final Inspection & Client Handover | John Doe | 2024-01-16 | 2024-01-31 | Delayed | 0%