## Home Management - Project Plan
Home Management - Project Plan (Compact)
Task ID | Task Description | Owner | Start Date | Due Date | Status | % Complete
HM-001 | Renovate Kitchen Area | Jane Smith | 2024-03-05 | 2024-04-15 | Ongoing | 68%
→ Remove old cabinets and countertops - In progress
→ Install new flooring - Scheduled for next week
HM-002 | Paint Living Room Walls | John Doe | 2024-03-10 | 2024-03-18 | Completed | 100%
HM-003 | Upgrade Bathroom Fixtures | Alice Johnson | 2024-03-15 | 2024-04-10 | Ongoing | 85%
→ Install new vanity and sink - Completed
→ Replace showerhead and faucet - In progress
HM-004 | Landscaping & Garden Refresh | Mike Brown | 2024-03-25 | 2024-05-15 | Delayed | 35%
→ Remove old shrubs and weeds - Delayed due to weather
→ Plant new flowers and grass seeds - Pending