## Home Management - Project Plan
Home Management - Project Plan (Detailed)
Task ID | Task Description | Responsible Person | Start Date | End Date | Status | % Complete
Phase 1: Project Initiation & Planning
PH1-001 | Define project scope and objectives | Project Manager | 2023-10-01 | 2023-10-05 | In Progress | 85%
PH1-002 | Identify key stakeholders and requirements | Project Manager, Team Lead | 2023-10-06 | 2023-10-15 | To Do | 0%
Phase 2: Design and Preparation
PH2-001 | Create detailed room layouts and design plans | Interior Designer, Architect | 2023-10-16 | 2023-11-05 | To Do | 0%
PH2-002 | Select materials, finishes, and fixtures | Project Manager, Supplier Coordinator | 2023-11-06 | 2023-11-15 | To Do | 0%
Phase 3: Construction & Installation
PH3-001 | Demolition and site preparation | Contractor Team, Safety Officer | 2023-11-16 | 2023-11-25 | To Do | 0%
PH3-002 | Structural modifications and framing | Carpentry Team, Electrician, Plumber | 2023-11-26 | 2023-12-15 | To Do | 0%
Phase 4: Finishing & Handover
PH4-001 | Painting, flooring, and wall finishes | Painter Team, Flooring Installer | 2023-12-16 | 2024-01-15 | To Do | 0%
PH4-002 | Installation of lighting, electrical, and plumbing fixtures | Electrician, Plumber, HVAC Technician | 2024-01-16 | 2024-01-31 | To Do | 0%
Phase 5: Final Review & Project Close
PH5-001 | Quality inspection and defect resolution | Quality Manager, Project Manager | 2024-02-01 | 2024-02-15 | To Do | 0%
PH5-002 | Final walkthrough and client sign-off | Project Manager, Client Representative | 2024-02-16 | 2024-03-15 | To Do | 0%
Total Project Duration: | [5 empty] | 2023-10-01 to 2024-03-15
Notes:
Status indicators: To Do, In Progress, Completed
% Complete reflects estimated progress based on milestone completion.
Adjust dates and responsibilities as needed during project execution.