## Worksheet
Home Management - Project Plan (Extended)
Task ID | Task Name | Owner | Start Date | End Date | Status | % Complete | Description/Notes
T001 | Project Initiation & Planning | Home Manager | 2024-04-01 | 2024-04-15 | Pending | 15% | Define goals, scope, resources, and timeline for home improvements.
T002 | Kitchen Renovation Phase 1 | Contractor A | 2024-04-16 | 2024-05-31 | In Progress | 65% | Demolition, electrical and plumbing upgrades.
T003 | Bathroom Remodel - Master | Contractor B | 2024-05-15 | 2024-07-15 | Pending | 1% | Design approval and material procurement.
T004 | Living Room Flooring Installation | Home Manager & Crew | 2024-06-15 | Prepare subfloor, install hardwood, finish sanding.
T005 | Backyard Deck Construction | Contractor C | 2024-07-16 | Foundation, framing, decking and railing completion.
T006 | Smart Home Integration | IT Technician | 2024-08-15 | 2024-09-30 | Pending | Install security system, lighting automation, climate control.
T010 | Final Inspections & Handover | Home Manager | 2024-10-01 | 2024-10-15 | Pending | Verify all work meets standards, obtain sign-off, document completion.
Total Tasks: | [5 empty] | 7 | Overall Progress: 32% Complete