## Worksheet
Home Management - Project Plan - Financial View
Task / Category | Budget (USD) | Actual Spend (USD) | Remaining Budget (USD) | Status
Painting Interior Walls | $1,200.00 | $950.00 | $250.00 | In Progress
Kitchen Cabinets Replacement | $4,500.00 | $3,800.00 | $700.00 | On Hold
Bathroom Tile & Fixtures Upgrade | $3,200.00 | $2,650.00 | $550.00 | In Progress
Hardwood Floor Installation (Living Room) | $2,800.00 | $1,950.00 | $850.00 | Delayed
Heating & Cooling System Upgrade | $6,500.00 | $5,400.00 | $1,100.00 | In Progress
Roof Shingle Replacement (Partial) | $3,800.00 | $3,500.00 | $300.00 | In Progress
Lawn & Garden Maintenance (Annual) | $1,500.00 | $980.00 | $520.00 | In Progress
Smart Thermostat & Security System | $1,850.00 | $1,340.00 | $510.00 | On Hold
Total Budget Summary | $24,650.00 | $20,570.00 | $4,080.00 | Remaining Funds Available
Notes:Budgets are projected monthly. Actual spends updated weekly. Projects with "On Hold" status may be resumed based on seasonal availability.