## Worksheet
Home Management - Freelancer Project Plan
Task | Description | Start Date | Due Date | Status | Assigned To
Define Project Scope | Outline all home improvement goals and priorities. | 2024-01-05 | 2024-01-10 | In Progress | Alice Johnson
Design Layout & Drafts | Create visual blueprints for room renovations. | 2024-01-11 | 2024-01-25 | To Do | Bob Smith
Procure Materials | Order supplies and equipment for all phases. | 2024-01-26 | 2024-02-15 | To Do | Claire Davis
Begin Kitchen Renovation | Demolition, cabinetry, countertop installation. | 2024-02-16 | 2024-03-15 | To Do | Daniel Lee
Bathroom Remodeling | Tile work, plumbing upgrades, fixtures. | 2024-03-16 | 2024-04-15 | To Do | Eva Martinez
Landscape & Exterior Upgrades | Landscaping, fencing, driveway repair. | 2024-04-16 | 2024-05-31 | To Do | Felix Brown
Final Inspections & Cleanup | Verify work quality and conduct thorough cleanup. | 2024-06-01 | 2024-06-15 | To Do | Alice Johnson
Total Duration: | 6 months (Jan 5, 2024 – Jun 15, 2024)
Project Notes
This project plan is designed for efficient home management by a freelancer team.
All milestones are tracked weekly, with status updates communicated every Monday.
Budget allocation is monitored monthly via shared financial dashboard.