## Home Management - Project Plan
Home Management Project Plan
Large Business Style ¦ Comprehensive Task Tracking & Timeline Overview
Task ID | Task Description | Assigned To | Start Date | End Date | Status | Budget (USD)
T001 | Design Home Renovation Layout | Alex Morgan | 2024-06-05 | 2024-06-15 | In Progress | $8,500.00
T002 | Procure Building Materials | Sarah Chen | 2024-06-16 | 2024-07-15 | Pending | $35,800.00
T003 | Foundation & Structural Work | James Reed (Contractor) | 2024-07-16 | 2024-09-30 | Pending | $78,450.00
T004 | Electrical & Plumbing Installation | Lisa Torres (Subcontractor) | 2024-10-01 | 2024-11-30 | Pending | $56,780.00
T005 | Interior Finishing & Painting | Robert Kim (Team Lead) | 2024-12-01 | 2025-01-31 | Pending | $45,980.00
T006 | Furniture & Appliance Installation | Emily Patel (Logistics) | 2025-02-01 | 2025-03-15 | Pending | $37,640.00
T007 | Final Inspection & Handover | David Wilson (Project Manager) | 2025-03-16 | 2025-04-30 | Pending | $12,499.99
Total Project Budget: | [5 empty] | $375,649.99