## Home Management - Project Plan
Purpose:Home Management
Template Type:Project Plan
Style/Version:Multi Page
Date:
Page:1 of 3
Project Plan Summary
Task ID | Task Description | Responsible Person | Status | Start Date | End Date | Budget (USD)
P-001 | Kitchen Renovation | John Doe | Planning | 2025-01-15 | 2025-04-30 | $8,500.00
P-017 | Bathroom Remodeling | Jane Smith | In Progress | 2025-02-14 | 2025-06-30 | $14,750.00
P-198 | Landscaping & Lawn Care | Mike Johnson | Scheduled | 2025-03-21 | 2025-07-15 | $3,675.00
P-433 | Smart Home Integration | Sarah Lee | Not Started | 2025-04-18 | 2025-10-31 | $6,899.75
P-776 | Furniture Procurement & Assembly | David Brown | In Progress | 2025-03-10 | 2025-08-14 | $9,456.33
Project Timeline (Gantt Chart View)
Task | Jan | Feb | Mar | Apr | May | Jun
Kitchen Renovation (P-001) | █ | █ | █ | ██ | ██ | ██
Bathroom Remodeling (P-017) |  | █ | █ | ██ | ██ | ██
Landscaping & Lawn Care (P-198) |  |  | █ | ██ | ██ | █
Smart Home Integration (P-433) |  |  |  | █ | ██ | ███
Key Milestones & Deliverables
Milestone | Due Date | Status
Design Approval - Kitchen & Bathroom | 2025-01-31 | In Progress (75%)
Flooring & Tile Installation Complete | 2025-04-15 | Pending Review (98%)
Final Inspection & Handover of Renovated Areas | 2025-07-31 | Not Started (0%)
Scheduled Smart Home System Testing Phase | 2025-10-15 | Not Started (0%)