## Home Management Project Plan
Home Management Project Plan
Task ID | Task Description | Assigned To | Status | Start Date | Due Date | Budget (USD)
HM-001 | Kitchen Renovation | Jane Smith | In Progress | 2024-04-01 | 2024-05-31 | $8,500.00
HM-002 | Bathroom Remodeling | Mike Johnson | Not Started | 2024-05-15 | 2024-07-31 | $6,750.00
HM-003 | Patio Construction | Lisa Brown | Not Started | 2024-06-15 | 2024-08-31 | $5,200.00
HM-004 | Landscaping and Lawn Care | Daniel Lee | In Progress | 2024-03-25 | 2024-11-30 | $3,800.00
HM-005 | Interior Painting (All Rooms) | Sarah Williams | Not Started | 2024-07-15 | 2024-11-30 | $4,950.00
HM-006 | Smart Home System Installation | Chris Davis | In Progress Status: In Progress
Total Project Budget | [5 empty] | $34,500.00