## Worksheet
Task ID | Task Description | Assigned To | Start Date | Due Date | Status | % Complete(Progress)
#001 | Renovate Kitchen Area | John Smith | 2025-04-01 | 2025-06-30 | In Progress | 65%
#002 | Install Smart Lighting System | Sarah Johnson | 2025-04-15 | 2025-05-15 | In Progress (Delayed) | 40%
#003 | Upgrade HVAC System | Mike Brown | 2025-05-10 | 2025-07-15 | Pending Approval | 10%
#004 | Paint Living Room and Hallway | Lisa Davis | 2025-06-15 | 2025-06-30 | Scheduled | 0%
#005 | Install Garden Irrigation System | David Wilson | 2025-07-01 | 2025-07-14 | Scheduled | 0%
#006 | Upgrade Home Security System | Emily Taylor | 2025-06-25 | 2025-07-18 | Scheduled | 0%
Overall Project Progress: | [5 empty] | 42%