## Worksheet
Project Name | Task Description | Start Date | End Date | Status | Assigned To | Budget (USD)
Home Renovation & Maintenance Plan - Summary View
Kitchen Remodel | Demolition of old cabinets and flooring | 2025-04-01 | 2025-04-05 | Completed | Jane Doe | 850
| Cabinet installation and countertop fitting | 2025-04-10 | 2025-04-18 | In Progress | John Smith | 3,200.00
| Plumbing and electrical updates | 2025-04-19 | 2025-04-23 | In Progress | Mike Johnson | 1,850.00
Bathroom Upgrade | Tile removal and wall repair | 2025-04-15 | 2025-04-17 | Completed | Sarah Lee | 675
| Bathroom fixture installation and sealant work | 2025-04-24 | 2025-04-30 | In Progress | Mike Johnson | 1,980.00
Landscaping & Exterior Repair | Front yard grading and sodding | 2025-05-01 | 2025-05-10 | Delayed | Jane Doe | 1,437.50
| Deck refinishing and safety inspection | 2025-05-12 | 2025-05-18 | Delayed | John Smith | 976.4
Total Project Budget: | [5 empty] | $11,975.30