## Home Management - Project Plan
Task ID | Task Description | Assigned To | Status | Start Date | End Date | Priority
101 | Kitchen Renovation Planning | Jane Doe | To Do | 2023-10-05 | 2023-10-15 | High
102 | Bathroom Plumbing Inspection | John Smith | In Progress | 2023-10-06 | 2023-10-18 | Medium
103 | Lawn Mowing Schedule Setup | Sarah Johnson | In Progress | 2023-10-07 | 2023-11-30 | Low
104 | Garden Design & Planting | Lisa Brown | To Do | 2023-10-15 | 2023-11-05
105 | Maintain HVAC System | Mike Wilson | Completed | 2023-10-03 | 2023-10-04
106 | Purchase New Appliances (Refrigerator) | Jane Doe | On Hold | 2023-10-18 | 2023-11-05
107 | Flooring Replacement (Living Room) | David Lee | To Do | 2023-10-25 | 2023-11-15
108 | Schedule Roof Inspection & Maintenance | John Smith | In Progress | 2023-10-09 | 2023-11-15
109 | Paint Interior Walls (Bedroom) | Sarah Johnson | To Do | 2023-10-30 | 2023-11-18
110 | Clean Gutters & Downspouts | Mike Wilson | To Do | 2023-10-20 | 2023-10-31
Note:This project plan template is designed for home management and can be exported to Excel or other spreadsheet software. Status updates should be reviewed weekly.