## Worksheet
Task ID | Task Name | Assigned To | Start Date | Due Date | Status | % Complete
T001 | Kitchen Renovation | John Doe | 2023-10-01 | 2023-12-15 | Ongoing | 65%
T002 | Paint Living Room | Jane Smith | 2023-11-05 | 2023-11-18 | Completed | 100%
T003 | Install New Flooring | Mike Johnson | 2023-11-20 | 2024-01-10 | Ongoing | 45%
T004 | Update HVAC System | Lisa Brown | 2023-12-01 | 2023-12-31 | Delayed | 70%
T005 | Landscaping and Garden Design | Tom Wilson | 2024-01-15 | 2024-03-31 | Completed | 100%
T006 | Smart Home Integration | Sarah Lee | 2024-02-15 | 2024-03-31 | Ongoing | 85%
T007 | Garage Organization System | Daniel Clark | 2023-11-10 | 2023-12-15 | Completed | 100%
T008 | Bathroom Remodel - Master Suite | Emily Davis | 2023-12-15 | 2024-03-15 | Ongoing | 55%
T009 | Interior Lighting Upgrade | Chris Evans | 2024-01-20 | 2024-03-15 | Delayed | 65%
T010 | Final Inspection & Handover | Project Manager | 2024-03-25 | 2024-03-31 | Completed | 100%