## Worksheet
Home Management Project Template - Financial View
Project Phase | Budget Allocation ($) | Actual Spend ($) | Remaining Budget ($) | Status | Notes
Initial Planning | 2,000.00 | 1,850.00 | 150 | On Track | Preliminary assessments completed.
Interior Renovation | 15,000.00 | 12,350.00 | 2,650.00 | Delayed (Minor) | Material delivery delayed by 3 days.
Appliance Upgrade | 8,500.00 | 8,425.00 | 75 | On Track | All appliances installed and tested.
Landscaping & Exterior | 6,000.00 | 5,275.00 | 725 | On Track | Lawn seeding completed.
Miscellaneous Expenses | 1,500.00 | 895 | 605 | On Track | Awaiting final vendor invoices.
Total | 33,000.00 | 28,795.00 | 4,205.00 | Remaining budget available for adjustments.