## Worksheet
Home Management Project Timeline
Task ID | Task Description | Owner | Start Date | Due Date | Status | % Complete
#001 | Initial Home Assessment & Planning | Sarah Johnson | 2025-04-01 | 2025-04-15 | In Progress | 65%
#002 | Kitchen Renovation Design Approval | Michael Chen | 2025-04-16 | 2025-04-30 | Pending | 15%
#003 | Plumbing System Inspection & Upgrade | Daniel Rodriguez | 2025-04-18 | 2025-05-15 | In Progress | 40%
#004 | Bathroom Remodeling - Demolition Phase | Jessica Williams | 2025-05-16 | 2025-06-15 | Pending | 3%
#005 | Electrical System Upgrade & Safety Check | Robert Thompson | 2025-05-18 | 2025-06-18 | Pending | 0%
#006 | Wall & Ceiling Painting (Interior) | Amy Patel | 2025-06-19 | 2025-07-18 | Pending | 0%
#007 | Flooring Installation (Main Living Areas) | James Brown | 2025-06-25 | 2025-08-15 | Pending | 0%
#008 | Furnishings & Decor Finalization | Lisa Garcia | 2025-07-28 | 2025-08-31 | Pending | 0%
#009 | Final Walkthrough & Quality Inspection | Sarah Johnson | 2025-08-26 | 2025-09-14 | Pending | 0%
#010 | Project Handover & Client Onboarding | Sarah Johnson | 2025-09-15 | 2025-09-30 | Pending | 0%
Total Tasks:10 ¦In Progress:2 ¦Pending:8
Last Updated: April 5, 2025