## Worksheet
Home Management - Project Timeline - Analysis View
Task ID | Task Name | Description | Start Date | End Date | Status | Priority | Budget (USD)
T001 | Foundation Preparation | Lay foundation and prepare ground for construction. | 2023-10-05 | 2023-10-15 | Delayed | High | $4,500.00
T002 | Structural Framing | Install main frame and roof structure. | 2023-10-16 | 2023-11-15 | In Progress | High | $9,800.00
T003 | Plumbing Installation | Run pipes and install fixtures. | 2023-11-16 | Not Started
T004 | Electrical Wiring | Install electrical system and outlets. | 2023-11-30