## Worksheet
Home Management - Project Timeline (Client View)
Project Overview & Milestone Tracking
Task ID | Task Description | Assigned To | Start Date | Due Date | Status
T001 | Initial Site Assessment & Survey | Laura Thompson - Project Manager | 2024-03-15 | 2024-03-18 | Completed
T002 | Design Concept Approval (Interior & Exterior) | James Reed - Lead Designer | 2024-03-19 | 2024-03-25 | In Progress
T003 | Material Selection & Procurement Order | Sophia Martinez - Procurement Specialist | 2024-03-26 | 2024-04-15 | Pending
T004 | Foundation & Structural Framing Phase 1 | Michael Chen - Site Supervisor | 2024-04-16 | 2024-05-15 | Pending
T005 | Electrical & Plumbing Rough-In Installation | David Wilson - Lead Electrician/Plumber | 2024-05-16 | 2024-06-15 | Pending
T006 | Drywall Installation & Insulation | Emma Brown - Construction Crew Lead | 2024-06-16 | 2024-07-15 | Pending
T007 | Finishing & Fixture Installation (Cabinets, Floors) | James Reed - Lead Designer | 2024-07-16 | 2024-08-15 | Pending
T008 | Final Inspections & Client Walkthrough | Laura Thompson - Project Manager | 2024-08-16 | 2024-08-31 | Pending
Project Status as of March 15, 2024 ¦ Client View – Updated in Real-Time