## Worksheet
Home Management Project Timeline
Task ID | Task Name | Description | Start Date | End Date | Status | Assigned To
#HT-001 | Initial Planning & Scope Definition | Define project goals, deliverables, and key milestones. | 2024-03-01 | 2024-03-15 | In Progress | Jane Smith
#HT-002 | Home Inspection & Assessment | Conduct detailed inspection of all rooms and systems. | 2024-03-16 | 2024-03-31 | Pending | Mike Johnson
#HT-003 | Renovation Planning & Design Approval | Finalize design plans and obtain stakeholder approval. | 2024-04-01 | 2024-04-15 | Pending | Lisa Brown
#HT-004 | Electrical System Upgrade | Replace outdated wiring and upgrade outlets. | 2024-04-16 | 2024-05-31 | Pending | Daniel Lee
#HT-005 | Plumbing System Repair & Enhancement | Fix leaks, replace old pipes, and improve water efficiency. | 2024-06-01 | 2024-07-15 | Pending | Sophia Garcia
#HT-006 | Painting & Finishing Interior Spaces | Apply primer and paint to all walls and ceilings. | 2024-07-16 | 2024-08-31 | Pending | Alex Turner
#HT-007 | Appliance Installation & Testing | Install new kitchen and laundry appliances. | 2024-09-01 | 2024-10-15 | Pending | Nina Patel
#HT-008 | Final Inspection & Handover Preparation | Conduct final quality check and prepare handover documents. | 2024-10-16 | 2024-11-30 | Pending | Jane Smith
#HT-009 | Project Completion & Review Meeting | Final review, client feedback, and closure of project. | 2024-12-01 | 2024-12-15 | Pending | All Team Members
#HT-010 | Warranty & Maintenance Documentation | Create and distribute maintenance manuals and contact info. | 2024-12-16 | 2024-12-31 | Pending | Daniel Lee
This timeline is generated for Home Management Project. Last updated on.