## Worksheet
Home Management - Project Timeline (Employee View)
Task ID | Task Name | Assigned To | Start Date | End Date | Status | Description
#HT-001 | Interior Painting (Living Room) | Sarah Johnson | 2025-04-05 | 2025-04-10 | In Progress | Repaint living room walls with modern beige finish.Use eco-friendly paint.
#HT-002 | Bathroom Renovation - Tiling | James Reed | 2025-04-11 | 2025-04-18 | Pending | Install ceramic tiles on floor and walls.Supplies ordered; awaiting delivery.
#HT-003 | Laundry Room Upgrade | Linda Carter | 2025-04-15 | 2025-04-21 | Pending | Install new shelving and upgrade washer/dryer.Equipment installation on hold pending inspection.
#HT-004 | Kitchen Countertop Installation | Marcus Lee | 2025-04-18 | 2025-04-25 | Pending | Install quartz countertops and edge sealing.Material delivery scheduled for 4/17.
#HT-005 | Backyard Landscaping | Emily White | 2025-04-20 | 2025-04-30 | Pending | Plant new flowers, install irrigation system.Soil prep completed; planting starts next week.