## Worksheet
Home Management Project Timeline
Task ID | Task Name | Description | Start Date | End Date | Status | Assigned To(Role)
HT-001 | House Inspection & Assessment | Conduct full visual inspection and structural evaluation of the property. | 2024-06-05 | 2024-06-15 | Completed | John Doe (Property Manager)
HT-002 | Renovation Planning | Create detailed renovation plan including scope, materials, and budget. | 2024-06-16 | 2024-07-15 | In Progress | Jane Smith (Project Lead)
HT-003 | Kitchen Remodel | Demolition, cabinetry installation, countertop replacement. | 2024-07-16 | 2024-11-30 | In Progress | Mike Johnson (Contractor)
HT-004 | Bathroom Renovation | Replace fixtures, tile work, ventilation upgrade. | 2024-12-01 | 2025-03-31 | Delayed | Sarah Lee (Contractor)
HT-005 | Flooring Installation | Lay hardwood flooring in living room, dining area, and hallways. | 2024-12-15 | 2025-03-15 | Delayed | Alex Brown (Flooring Specialist)
HT-006 | Interior Painting | Paint walls, trim, and ceilings in all rooms. | 2025-03-16 | 2025-04-30 | Completed | Lisa Chen (Painter)
HT-007 | Final Inspection & Handover | Inspect all work, address punch list items, hand over keys to homeowner. | 2025-05-01 | 2025-05-15 | In Progress | John Doe (Property Manager)