## Worksheet
Home Management - Project Timeline (Freelancer Style)
Task | Description | Start Date | End Date | Status | Assigned To
Foundation Work | Laying the foundation for the new home structure. | 2024-04-01 | 2024-04-15 | In Progress | Alex Morgan
Wall Construction | Building exterior and interior walls. | 2024-04-16 | 2024-05-10 | Pending | Jessica Lee
Roof Installation | Installing the roof structure and shingles. | 2024-05-11 | 2024-05-25 | Pending | Daniel Kim
Plumbing & Electrical Rough-In | Installing pipes and wiring before drywall. | 2024-05-26 | 2024-06-10 | Pending | Laura Chen
Drywall & Painting | Applying drywall and finishing with paint. | 2024-06-11 | 2024-07-05 | Pending | Marcus Taylor
Flooring Installation | Laying hardwood and tile flooring. | 2024-07-06 | 2024-07-25 | Pending | Sophia Patel
Cabinetry & Fixtures | Installing kitchen cabinets and bathroom fixtures. | 2024-07-26 | 2024-08-15 | Pending | Jamal Brooks
Final Inspection & Cleanup | Quality check and final cleaning before handover. | 2024-08-16 | 2024-08-31 | Pending | All Team Members