## Worksheet
Home Management - Project Timeline
Task ID | Task Description | Assigned To | Start Date | End Date | Status | Budget ($)
#001 | Foundation Work & Site Preparation | John Doe (Contractor) | 2025-03-01 | 2025-03-15 | In Progress | $4,800.00
#002 | Structural Framing (Walls & Roof) | Mike Smith (Builder) | 2025-03-16 | 2025-04-15 | In Progress | $9,200.00
#003 | Electrical & Plumbing Rough-In | Lisa Wang (Electrician) | 2025-04-16 | 2025-05-15 | Completed | $6,300.00
#004 | Insulation & Drywall Installation | Daniel Reed (Plasterer) | 2025-05-16 | 2025-06-15 | In Progress | $7,400.00
#005 | Painting & Finishing Touches | Sarah Thompson (Painter) | 2025-06-16 | 2025-07-10 | Completed | $4,950.00
#006 | Flooring Installation (Hardwood & Tile) | James Carter (Floor Specialist) | 2025-07-11 | 2025-08-15 | Delayed | $8,600.00
#007 | Final Inspection & Approval | Emma Brooks (Inspector) | 2025-08-16 | 2025-08-31 | Completed | $1,500.00
#008 | Moving In & Final Walkthrough | Homeowner (You) | 2025-09-01 | 2025-09-15 | Completed | $3,750.00
Total Project Budget:$51,500.00
Current Progress:87.5%