## Worksheet
Home Management Project Timeline
Task ID | Task Description | Assigned To | Start Date | Due Date | Status
101 | Kitchen Remodeling Preparation | John Doe | 2023-10-05 | 2023-10-15 | In Progress
102 | Ceiling Repair in Living Room | Jane Smith | 2023-10-10 | 2023-10-25 | Not Started
103 | Bathroom Renovation - Demolition Phase | Mike Johnson | 2023-10-20 | 2023-11-05 | Not Started
104 | Painting Interior Walls - First Layer | Sarah Wilson | 2023-11-05 | 2023-11-20 | Not Started
105 | Flooring Installation - Kitchen & Hallway | Lisa Brown | 2023-11-15 | 2023-12-05 | Not Started
106 | Furniture Assembly and Placement | Daniel Lee | 2023-12-06 | 2023-12-15 | Not Started
107 | Cleaning and Final Inspection | All Team Members | 2023-12-16 | 2023-12-20 | Not Started