## Worksheet
Task ID | Task Description | Start Date | End Date | Status | Responsible Person | Priority
T001 | Define Home Renovation Scope | 2024-04-05 | 2024-04-15 | In Progress | Jane Doe | High
T002 | Obtain Permits and Approvals | 2024-04-16 | 2024-05-15 | Pending | John Smith | High
T003 | Hire General Contractor | 2024-05-16 | 2024-05-31 | Pending | Jane Doe | High
T004 | Demolition and Site Prep | 2024-06-01 | 2024-06-15 | Pending | Mike Brown | High
T005 | Framing and Roof Installation | 2024-06-16 | 2024-07-15 | Pending | Mike Brown | High
T006
T007 | Electrical and Plumbing Rough-In | 2024-07-16 | 2024-08-15 | Pending | Sam Wilson | Medium
T008
T009 | Insulation and Drywall Installation | 2024-08-16 | 2024-09-15 | Pending | Lisa Green | Medium
T010
T011 | Painting and Finishes | 2024-09-16 | 2024-10-31 | Pending | Lisa Green | Medium
T012
T013 | Landscaping and Exterior Work | 2024-11-01 | 2024-11-30 | Pending | Daniel Reed | Low
T014