## Worksheet
Home Management Project Timeline
Phase | Task | Start Date | End Date | Status | Responsible Party
Phase 1: Planning & Assessment
Planning | Define project scope and objectives | 2023-10-01 | 2023-10-15 | In Progress | Jane Doe
Planning | Finalize scope and budget approval | 2023-10-15 | 2023-10-18 | Milestone Reached | Jane Doe / Finance Team
Phase 2: Design & Approval
Design | Create interior layout and design concepts | 2023-10-19 | 2023-11-05 | Pending Approval | Mike Johnson (Designer)
Design | Client sign-off on final design | 2023-11-05 | 2023-11-07 | Milestone Reached | Jane Doe / Client
Phase 3: Procurement & Preparation
Procurement | Order materials and fixtures | 2023-11-08 | 2023-11-25 | In Progress | Peter Lee (Procurement)
Phase 4: Construction & Installation
Execution | Demolition and structural prep | 2023-11-26 | 2023-12-05 | Pending Start | Ryan Taylor (Contractor)
Execution | Install flooring and wall treatments | 2023-12-06 | 2023-12-15 | Milestone Reached | Ryan Taylor (Contractor)
Phase 5: Final Touches & Handover
Completion | Install lighting, fixtures, and décor | 2023-12-16 | 2024-01-05 | Pending Start | Lisa Chen (Interior Designer)
Completion | Final walkthrough and handover to homeowner | 2024-01-06 | 2024-01-15 | Milestone Reached | Jane Doe / Client Team
This project timeline is printable and intended for home management use. All dates are subject to change based on external factors. Project Status Legend: In Progress ¦ Pending Start ¦ Pending Approval ¦ Milestone Reached