## Worksheet
Home Management Project Timeline
Professional Template – Track Progress, Deliver on Time
Task | Description | Start Date | End Date | Status | Owner | Action
Planning & Design Phase | Develop layout, finalize materials, and approve design concepts. | 2024-04-01 | 2024-04-15 | In Progress | Jane Smith | Update
Structural Renovation | Demolition, framing, and foundation work. | 2024-04-16 | 2024-05-31 | In Progress | Mike Johnson | Update
Electrical & Plumbing Installation | Install wiring, outlets, fixtures; plumbing lines and connections. | 2024-06-01 | 2024-06-25 | Pending | Sarah Williams | Update
Interior Finishing | Wallpaper, paint, flooring, and cabinet installation. | 2024-06-26 | 2024-07-15 | Pending | Lisa Brown | Update
Final Inspection & Handover | Certification, safety checks, and client walkthrough. | 2024-07-16 | 2024-07-31 | Pending | James Wilson | Update