## Worksheet
Home Management - Quarterly Project Timeline
Task / Activity | Q1: January - March 2024 |  |  |  | Q2: April - June 2024 |  |  |  | Q3: July - September 2024 |  |  | Q4: October - December 2024
| Due Date | Status | Owner | Notes | Due Date | Status | Owner | Notes | Due Date | Status | Owner
Annual Home Inspection & Maintenance Plan Review | 2024-03-15 | Completed | John Doe | Due Date | Status | Owner | Notes
Kitchen Remodeling Phase 1 - Cabinets & Countertops | 2024-03-30 | In Progress | Sarah Miller
Roof Inspection and Repairs (Seasonal Check) | 2024-03-10 | Completed | Mike Johnson
Smart Home System Upgrade (Security & Lighting) | 2024-03-25 | Delayed | Lisa Chen
Backyard Landscaping & Irrigation Update | 2024-03-18 | Completed | Tina Wilson
Heating System Servicing & Filter Replacement | 2024-03-05 | Completed | Robert Kim