## Worksheet
Home Management - Project Timeline Report
Task ID | Task Description | Responsible Person | Start Date | End Date | Status | Milestones Achieved (%)(Progress)
HT001 | Kitchen Renovation Planning | Alice Johnson | 2024-03-05 | 2024-03-15 | In Progress | 65%
HT002 | Install New Cabinets & Countertops | Michael Brown | 2024-03-16 | 2024-04-10 | In Progress | 85%
HT003 | Purchase Appliances (Fridge, Oven) | Sarah Davis | 2024-03-18 | 2024-04-15 | In Progress | 75%
HT004 | Electrical Wiring Upgrade | Robert Wilson | 2024-03-15 | 2024-03-31 | Completed | 100%
HT005 | Paint Walls & Ceilings | Lisa Thompson | 2024-04-11 | 2024-04-30 | In Progress | 55%
HT006 | Lay New Flooring (Hardwood) | James Garcia | 2024-04-15 | 2024-05-15 | Delayed | 38%
HT007 | Final Inspections & Cleanup | Alice Johnson | 2024-05-16 | 2024-05-31 | Delayed | 5%