## Worksheet
Task ID | Task Description | Start Date | End Date | Status | Responsible Person
T001 | Renovate Kitchen Area | 2025-04-01 | 2025-04-15 | In Progress | Jane Smith
T002 | Install Smart Home System | 2025-04-16 | 2025-04-30 | To Do | Mike Johnson
T003 | Upgrade HVAC System | 2025-05-01 | 2025-05-14 | To Do | Sarah Lee
T004 | Paint Living Room & Hallway | 2025-05-15 | 2025-05-28 | To Do | Tom Brown
T005 | Landscaping & Garden Upgrade | 2025-06-01 | 2025-06-14 | To Do | Lisa Wong
T006 | Final Inspection & Handover | 2025-06-15 | 2025-06-30 | To Do | Jane Smith