## Worksheet
Home Management Project Timeline
Phase | Task | Start Date | End Date | Status
1. Planning | Define home management goals | 2024-04-05 | 2024-04-12 | Completed
| Create budget and resource plan | 2024-04-13 | 2024-04-19 | Completed
| Gather stakeholder feedback | 2024-04-20 | 2024-04-26 | In Progress
2. Design | Develop interior layout concept | 2024-04-27 | 2024-05-10 | In Progress
| Select materials and finishes | 2024-05-11 | 2024-05-17 | Pending
| Create 3D mockups and presentation | 2024-05-18 | 2024-05-24 | Pending
3. Execution | Procure materials and equipment | 2024-05-25 | 2024-06-10 | Pending
| Begin construction and installation | 2024-06-11 | 2024-07-15 | Pending
| Quality checks and adjustments | 2024-07-16 | 2024-07-31 | Pending
| Final walkthrough and approval | 2024-08-01 | 2024-08-15 | Pending
4. Review | Conduct post-completion evaluation | 2024-08-16 | 2024-08-31 | Pending
| Document lessons learned and future improvements | 2024-09-01 | 2024-09-15 | Pending
Total Duration |  |  |  | 2024-04-05 to 2024-09-15 (5 months)
Home Management Project Timeline • Startup Version • Generated on 2024-04-05