## Worksheet
Task | Start Date | End Date | Status | Responsible Person
Planning Phase: Define project scope and goals | 2023-10-01 | 2023-10-15 | In Progress | Jane Doe
Design: Create floor plans and layout sketches | 2023-10-16 | 2023-10-31 | Pending | John Smith
Procurement: Purchase materials and supplies | 2023-11-01 | 2023-11-15 | Pending | Alice Johnson
Construction: Begin renovation and installation | 2023-11-16 | 2024-01-31 | Pending | Robert Brown
Inspection and Quality Check | 2024-02-01 | 2024-02-15 | Pending | Jane Doe
Final Touches: Painting, cleaning, and décor setup | 2024-02-16 | 2024-03-15 | Pending | Alice Johnson
Project Completion and Handover | 2024-03-16 | 2024-03-31 | Pending | John Smith
Template Version:1.2 ¦Purpose:Home Management ¦Template Type:Project Timeline